## 1. Cover & Assumptions
AIdeology — Internal Pricing & Staffing Analysis
ADNOC Loyalty AI Programme · Subcontract to HPE · v0.1 DRAFT
INTERNAL — NOT FOR HPE OR ADNOC. Pricing model for AIdeology team only.
Date: 2026-04-30
How to use this workbook
• All blue-text cells are editable inputs (rates, allocations, durations, margins).
• All yellow-highlighted cells are key assumptions to confirm before sending pricing to HPE.
• All black-text cells are calculated formulas — do not overwrite.
• Green-text cells are links to other sheets in this workbook.
• Sheet 2: Roles & Rates — adjust daily costs and bill rates here.
• Sheet 3: Phase Staffing — adjust headcount and allocation % per phase.
• Sheet 4: Phase Effort & Cost — calculated from staffing × rates.
• Sheet 5: Other Costs — software, cloud, contingency.
• Sheet 6: Pricing Summary — adds AIdeology margin to derive Price to HPE.
• Sheet 7: Payment Milestones — 4-payment schedule tied to SOW deliverables.
• Sheet 8: Sensitivity — scenarios at 10k / 25k / 50k concurrency.
Global assumptions
Assumption | Value | Unit | Notes / source
Programme duration | 16 | weeks | Per SOW §5.1 — 3–4 month delivery, single-phase on-prem.
Working days per week | 5 | days | Standard.
Hours per working day | 8 | hours | Standard.
Currency | USD | — | Internal model; final pricing to HPE may be issued in AED or USD.
FX assumption (USD→AED) | 3.67 | rate | Pegged.
AIdeology target gross margin | 35% | % | Target margin on cost before HPE markup. Adjust for win-rate.
Contingency on direct cost | 10% | % | Buffer for unknowns (sandbox slip, pen-test rework, etc.).
Risk reserve (held back) | 5% | % | Held internally; not in price to HPE.
HPE markup (illustrative) | 20% | % | ILLUSTRATIVE only — HPE sets its own markup. Not in our pricing.
Concurrency baseline | 25k | scenario | Mid scenario per SOW §3.5. Sensitivity sheet covers 10k / 25k / 50k.
Important disclaimers
• Daily rates in Sheet 2 are PLACEHOLDER values for AIdeology to validate against actual cost structure.
• Headcount and allocation % per phase are AIdeology's first-pass sizing. Adjust based on actual team capacity.
• Voice provider on-prem cost (11Labs) on Sheet 5 is an estimate pending vendor quote.
• GPU loan from HPE is assumed at no charge for the bridge period; if HPE charges, add to Sheet 5.
• All non-personnel costs are estimates only; obtain firm quotes before issuing commercial annex to HPE.

## 2. Roles & Rates
Roles & Daily Rates
Daily rates in USD. Internal cost = AIdeology fully-loaded cost. Bill rate = what we charge HPE before margin applied at programme level (Sheet 6).
Role | Seniority | Internal cost / day (USD) | Bill rate / day (USD) | Notes
Engagement / Programme Manager | Senior | 1100 | 1850 | Single point of contact to HPE PMO; weekly governance.
Solution Architect (Lead) | Principal | 1100 | 2150 | Owns HLD/LLD; latency budget; sizing scenarios.
AI / LLM Engineer — Orchestration & Reasoning | Senior | 900 | 1750 | Markdown rules engine, FSM, tool-calling. LLM service, prompt management, guardrails.
Voice / Conversational Engineer | Senior | 900 | 1750 | 11Labs on-prem, fillers, barge-in.
Data & Integration Engineer | Senior | 950 | 1550 | Oracle DW views, local cache, PII masking pipeline. MCP server + 6 ADNOC adapters.
Frontend / UX Engineer | Mid | 800 | 1300 | Operator / Manager / Admin consoles.
DevOps / Platform Engineer | Senior | 950 | 1550 | Helm, Terraform, CI/CD, Grafana/Loki.
QA Engineer | Mid | 750 | 1200 | UAT pack, synthetic data, automated tests.
Security / Compliance Lead | Senior | 1100 | 1750 | PII residency, GDPR alignment, pen-test support.
Total roles in plan: 9

## 3. Phase Staffing
Phase Staffing — Person-weeks per Role per Phase
Each cell = (headcount × % allocation × phase duration in weeks). Edit headcount and allocation in the editable section below.
Role | P1 — Mobilisation & Discovery | P2 — Architecture & Prototype | P3 — Build (core + integrations) | P4 — Integration & Hardening | P5 — Pilot & Phase-1 Expansion | P6 — Hand-over & Hypercare | Total p-weeks
Phase duration (weeks) | 2 | 2 | 4 | 2 | 4 | 2 | —
Engagement / Programme Manager | 1 | 1 | 2.4 | 1.4 | 2.8 | 1 | 9.6
Solution Architect (Lead) | 2 | 2 | 3.2 | 1.2 | 1.6 | 0.6 | 10.6
AI / LLM Engineer — Reasoning | 1 | 2 | 8 | 4 | 2.4 | 0.8 | 18.2
Voice / Conversational Engineer | 1 | 1.6 | 8 | 2 | 2.4 | 0 | 15
Data Engineer | 1 | 1.6 | 3.2 | 1.6 | 2 | 0 | 9.4
Frontend / UX Engineer | 1 | 1.2 | 4 | 1.6 | 2 | 0 | 9.8
DevOps / Platform Engineer | 1.6 | 3.2 | 3.2 | 1.6 | 3.2 | 1 | 13.8
QA Engineer | 0 | 0 | 2 | 2 | 8 | 1 | 13
Security / Compliance Lead | 1 | 1 | 1.2 | 1 | 1.2 | 0 | 5.4
Total person-weeks per phase | 9.6 | 13.6 | 35.2 | 16.4 | 25.6 | 4.4 | 104.8
EDITABLE — Headcount and Allocation % per Role per Phase
Format per cell: HEADCOUNT × ALLOCATION%. Edit in the two sub-rows below per role.
Headcount per phase (number of people).
Role | P1 — Mobilisation & Discovery | P2 — Architecture & Prototype | P3 — Build (core + integrations) | P4 — Integration & Hardening | P5 — Pilot & Phase-1 Expansion | P6 — Hand-over & Hypercare
Engagement / Programme Manager | 1 | 1 | 1 | 1 | 1 | 1
Solution Architect (Lead) | 1 | 1 | 1 | 1 | 1 | 1
AI / LLM Engineer — Reasoning | 1 | 1 | 2 | 2 | 1 | 1
Voice / Conversational Engineer | 1 | 1 | 2 | 1 | 1 | 0
Data Engineer | 1 | 1 | 1 | 1 | 1 | 0
Frontend / UX Engineer | 1 | 1 | 1 | 1 | 1 | 0
DevOps / Platform Engineer | 1 | 2 | 1 | 1 | 1 | 1
QA Engineer | 0 | 0 | 1 | 1 | 2 | 1
Security / Compliance Lead | 1 | 1 | 1 | 1 | 1 | 0
Allocation % per phase (share of time on this programme).
Role | P1 — Mobilisation & Discovery | P2 — Architecture & Prototype | P3 — Build (core + integrations) | P4 — Integration & Hardening | P5 — Pilot & Phase-1 Expansion | P6 — Hand-over & Hypercare
Engagement / Programme Manager | 50% | 50% | 60% | 70% | 70% | 50%
Solution Architect (Lead) | 100% | 100% | 80% | 60% | 40% | 30%
AI / LLM Engineer — Reasoning | 50% | 100% | 100% | 100% | 60% | 40%
Voice / Conversational Engineer | 50% | 80% | 100% | 100% | 60% | 0%
Data Engineer | 50% | 80% | 80% | 80% | 50% | 0%
Frontend / UX Engineer | 50% | 60% | 100% | 80% | 50% | 0%
DevOps / Platform Engineer | 80% | 80% | 80% | 80% | 80% | 50%
QA Engineer | 0% | 0% | 50% | 100% | 100% | 50%
Security / Compliance Lead | 50% | 50% | 30% | 50% | 30% | 0%

## 4. Phase Effort & Cost
Phase Effort & Cost — Internal Cost basis
Cost per role per phase = person-weeks (Sheet 3) × days per week × internal cost/day (Sheet 2). Bill view repeats with bill rates.
A. INTERNAL COST (fully-loaded AIdeology cost)
Role | Cost / day | P1 — Mobilisation & Discovery | P2 — Architecture & Prototype | P3 — Build (core + integrations) | P4 — Integration & Hardening | P5 — Pilot & Phase-1 Expansion | P6 — Hand-over & Hypercare | Total cost | % of total
Engagement / Programme Manager | 500 | 2500 | 2500 | 6000 | 3500 | 7000 | 2500 | 24000 | 8.674%
Solution Architect (Lead) | 600 | 6000 | 6000 | 9600 | 3600 | 4800 | 1800 | 31800 | 11.49%
AI / LLM Engineer — Reasoning | 600 | 3000 | 6000 | 24000 | 12000 | 7200 | 2400 | 54600 | 19.73%
Voice / Conversational Engineer | 600 | 3000 | 4800 | 24000 | 6000 | 7200 | 0 | 45000 | 16.26%
Data Engineer | 500 | 2500 | 4000 | 8000 | 4000 | 5000 | 0 | 23500 | 8.493%
Frontend / UX Engineer | 400 | 2000 | 2400 | 8000 | 3200 | 4000 | 0 | 19600 | 7.083%
DevOps / Platform Engineer | 600 | 4800 | 9600 | 9600 | 4800 | 9600 | 3000 | 41400 | 14.96%
QA Engineer | 400 | 0 | 0 | 4000 | 4000 | 16000 | 2000 | 26000 | 9.396%
Security / Compliance Lead | 400 | 2000 | 2000 | 2400 | 2000 | 2400 | 0 | 10800 | 3.903%
Total internal cost per phase |  | 25800 | 37300 | 95600 | 43100 | 63200 | 11700 | 276700 | 100%

## 5. Other Costs
Other (non-personnel) Costs
Software, cloud, voice provider, travel, contingency. All values are placeholder estimates pending firm quotes.
Cost item | Unit cost | Quantity / months | Total cost | Phase trigger | Notes
11Labs on-prem licence (estimate) | 15000 | 4 | 60000 | P2–P6 | Pending vendor quote; viability under evaluation per SOW §7.1 A4.
LLM inference licence / model access | 8000 | 4 | 32000 | P2–P6 | Open-weights deployed on HPE infra; assume nominal licence fee.
Observability stack (Grafana Cloud / Loki) | 1500 | 4 | 6000 | P1–P6 | Hosted observability for the team during build.
CI/CD & repo hosting | 800 | 4 | 3200 | P1–P6 | GitHub Enterprise / equivalent.
Security tooling (SAST/DAST/SCA) | 2500 | 4 | 10000 | P1–P6 | Snyk / Checkmarx etc.
Pen-test (third-party) | 25000 | 1 | 25000 | P4 | External pen-test before pilot go-live.
Travel — UAE (per trip, 3 people, 5 days) | 9000 | 4 | 36000 | P1–P5 | On-site mobilisation, integration, UAT, pilot go-live.
Demo / event support (Make in the UAE) | 5000 | 1 | 5000 | P1 | Per Schedule A action.
Misc (printing, demos, contingencies) | 3000 | 4 | 12000 | All | Petty cash for the engagement.
Total other costs (subtotal) |  |  | 189200

## 6. Pricing Summary
Pricing Summary — From Internal Cost to Price-to-HPE
Walks the cost stack: personnel + non-personnel + contingency + AIdeology margin = Price to HPE. HPE markup shown for illustration only.
Component | Value (USD) | Notes
Personnel cost — internal (sum of phases) | 276700 | From Sheet 4 (cost basis).
Other costs — non-personnel | 189200 | From Sheet 5.
Subtotal — direct cost | 465900 | Personnel + non-personnel.
Contingency on direct cost | 46590 | % from Sheet 1.
Total fully-loaded cost | 512490 | Direct cost + contingency.
AIdeology margin on cost | 275956.1538 | Margin grossed up: price = cost / (1 - margin).
Price to HPE (excl. risk reserve) | 788446.1538 | What we propose to charge HPE.
Effective margin % | 35% | Should approximate target margin from Sheet 1.
ILLUSTRATIVE — HPE markup | 157689.2308 | HPE sets its own markup. This is for our internal awareness only.
ILLUSTRATIVE — Price to ADNOC (post-HPE markup) | 946135.3846 | What ADNOC may pay if HPE applies the assumed markup.
Risk reserve (held internally — not in price) | 25624.5 | Held at AIdeology level for genuine risk events.
Memo — net AIdeology gross margin after risk reserve | 250331.6538 | Useful internal management number.

## 7. Payment Milestones
Payment Milestones — Price-to-HPE distributed across 4 trigger events
Triggered by SOW deliverables. Total = 100% of Price to HPE. Sum check at the bottom must equal Price to HPE.
# | Milestone / trigger | % of price | Target week | Amount (USD) | Acceptance criteria
1 | Mobilisation & SOW signature (kickoff) | 25% | T + 0 | 197111.5385 | SOW signed; team mobilised within 48h; SOW Schedule A traceability accepted.
2 | Architecture acceptance + integration sandbox live | 30% | T + 4 wk | 236533.8462 | M3 (HLD accepted) + M5 (MCP server v1 + first 3 ADNOC integrations wired).
3 | Pilot go-live (limited cohort) | 30% | T + 12 wk | 236533.8462 | M9 (pilot go-live) — Subcontractor confirms deployment; HPE/ADNOC validate first 5 days.
4 | Final acceptance & hand-over | 15% | T + 16 wk | 118266.9231 | M11 (hand-over to HPE service ops + SLA validation period commenced).
| Sum check | 100% |  | 788446.1538
Indicative monthly cash-flow (months from kickoff)
Item | M0 (kickoff) | M1 | M2 | M3 (pilot go-live) | M4 (hand-over)
Cash IN (payments from HPE) | 197111.5385 | 236533.8462 | 0 | 236533.8462 | 118266.9231
Cash OUT (AIdeology cost burn, est.) | 0 | 100940 | 152360 | 131460 | 81140
Net cash flow | 197111.5385 | 135593.8462 | -152360 | 105073.8462 | 37126.9231
Cumulative net cash flow | 197111.5385 | 332705.3846 | 180345.3846 | 285419.2308 | 322546.1538
Note: cash-out assumes uniform burn within month; refine if monthly invoicing differs from phase boundaries.

## 8. Sensitivity
Sensitivity — Cost & Price by Concurrency Scenario
Three concurrency design points per SOW §3.5. Effort uplift modelled as a multiplier on personnel cost.
Scenario | Effort uplift | Personnel cost | Other costs uplift | Total fully-loaded cost | Notes
10k concurrent users | 0.85 | 235195 | 0.9 | 446022.5 | Lighter sizing; smaller cluster, fewer integrations stress points.
25k concurrent users (baseline) | 1 | 276700 | 1 | 512490 | Baseline assumed in main sheets.
50k concurrent users | 1.3 | 359710 | 1.2 | 645425 | Heavier sizing; more parallelism, additional NFR work.
Scenario | Total fully-loaded cost | Margin | Price to HPE | Δ vs baseline | Notes
10k concurrent users | 446022.5 | 240165.9615 | 686188.4615 | -12.97% | Lighter sizing; smaller cluster, fewer integrations stress points.
25k concurrent users (baseline) | 512490 | 275956.1538 | 788446.1538 | 0% | Baseline assumed in main sheets.
50k concurrent users | 645425 | 347536.5385 | 992961.5385 | 25.94% | Heavier sizing; more parallelism, additional NFR work.