## 0. Executive Summary
AIdeology × e& — SMB Internal Pricing Summary
One page. All the numbers that matter. Detail in tabs 1-10.
A. WHAT ARE WE BUILDING?
We build an AI platform for e& that lets small businesses subscribe to AI agents (Customer, Sales, Comms, Finance, Ops, People).
v
We earn money two ways: (1) fixed fees for building each wave, and (2) a % of every SMB subscription (revenue share) forever.
B. WHAT DOES IT COST US?
Wave 1 cost (platform + Customer Agent) |  | Waves 2-4 cost (5 more agents) |  | Total cost (all waves)
688572.5 |  | 1262800 |  | 1951372.5
C. WHAT DO WE CHARGE e&? (fixed fees)
Wave 1 price to e& (40% margin) |  | Waves 2-4 price to e& (45% margin) |  | Total fixed-fee envelope
1147620.8333 |  | 2296000 |  | 3443620.8333
Our margin on Wave 1: | 40% | Our margin on Waves 2-4: | 45%
D. RECURRING REVENUE — our % of every SMB subscription
| Year 1 | Year 2 | Year 3 | 3-Year Total
Paying SMBs (avg) | 375 | 1500 | 3125
e& gross revenue | 270000 | 1170000 | 2625000 | 4065000
Our rev-share (15%) | 40500 | 175500 | 393750 | 609750
E. TOTAL AIDEOLOGY REVENUE (3 years)
| Year 1 | Year 2 | Year 3 | 3-Year Total
Fixed fees (building) | 1629911.7424 | 1394600 | 419109.0909 | 3443620.8333
Rev-share (recurring) | 40500 | 175500 | 393750 | 609750
TOTAL | 1670411.7424 | 1570100 | 812859.0909 | 4053370.8333
F. THREE WAYS TO PRICE THE DEAL
| Option A: Full price | Option B: Hybrid | Option C: Land & expand
Up-front fee (Wave 1) | 1147620.8333 | 500000 | 250000
Rev-share % | 10% | 18% | 20%
Best for | AIdeology cash flow | Balanced risk/reward | Easiest to sell
Risk | Hardest to close | Moderate | We lose money on Wave 1
G. KEY RISK — our cost vs. what we proposed in the commercial framework
The commercial framework we showed e& quoted $150K-$250K for the implementation. Our internal model shows it actually costs us $689K.
If we charge $250K, we lose ~$439K on Wave 1. We need ~2.2 years of rev-share to break even. This is only viable if we believe in the subscriber ramp.
Recommendation: negotiate a higher up-front fee ($500K+) OR a higher rev-share (18-20%) to protect our margins. See Sheet 7 for the three options.

## 1. Cover & Assumptions
AIdeology — Internal Pricing & Staffing Analysis
e& B2B Acceleration · Pillar 01 — SMB Platform-Centric Agentic Solutions · v0.1 DRAFT
INTERNAL — NOT FOR e&. Pricing model for AIdeology team only.
Date: 2026-05-10
How to use this workbook
• All blue-text / yellow-shaded cells are editable inputs (rates, allocations, durations, margins, subscriber ramp).
• All green-text cells are formulas linking other sheets — do not overwrite.
• Sheet 2: Roles & Rates — adjust daily costs and bill rates here.
• Sheet 3: Phase Staffing — Wave 1 (SMB Launch) headcount and allocation per phase.
• Sheet 4: Phase Effort & Cost — calculated from staffing × rates.
• Sheet 5: Other Costs — software, cloud, voice, WhatsApp BSP, contingency.
• Sheet 6: Wave 2-4 Build Costs — Sales+Comms, Finance+Ops, People agentic solutions (incremental on top of platform).
• Sheet 7: Pricing Summary — fixed implementation fee per wave + AIdeology margin.
• Sheet 8: Revenue Share Model — subscriber ramp × ARPU × rev-share % over 3 years.
• Sheet 9: Payment Milestones — Wave 1 stage-gated payments.
• Sheet 10: Sensitivity — adoption × rev-share scenarios for AIdeology 3-year revenue.
Global assumptions
Assumption | Value | Unit | Notes / source
Wave 1 (SMB Launch) duration | 15 | weeks | Per launch plan: W1-15 covers M1 foundations → M6 GA + hypercare ramp.
Working days per week | 5 | days | Standard.
Hours per working day | 8 | hours | Standard.
Currency | USD | — | Internal model; final pricing to e& may be issued in AED or USD.
FX assumption (USD→AED) | 3.67 | rate | Pegged.
AIdeology target gross margin (Wave 1 fixed fee) | 40% | % | Higher than ADNOC: SMB platform is reusable IP; we own the blueprint stack.
Contingency on direct cost | 10% | % | Buffer for unknowns (sandbox slip, BSP approval delays, beta iteration).
Risk reserve (held back) | 5% | % | Held internally; not in price to e&.
Wave 2-4 target gross margin (per-wave fee) | 45% | % | Reusing platform — higher margin justified.
Subscriber ramp — start month (after GA) | 1 | month | Month 1 = first subscribers post GA. Cash-in starts Month 4 of programme.
ARPU per SMB tenant (USD/month) | 60 | $/mo | Per JSX commercial framework rev forecast ($60/mo blended).
Rev-share % to AIdeology (mid) | 15% | % | Range 10-20%, mid scenario 15%. Sensitivity sheet covers low/mid/high.
Annual churn rate | 20% | % | Net of upgrades. ~5%→3%/mo per JSX → ~20% annualised conservative.
Rev-share term (years) | 3 | years | Per JSX: 24-month minimum partnership, modelled to year 3.
Important disclaimers
• Daily rates in Sheet 2 are PLACEHOLDER values for AIdeology to validate against actual cost structure.
• Headcount and allocation per phase are AIdeology's first-pass sizing. Adjust based on actual team capacity.
• Wave 2-4 sizing in Sheet 6 assumes the base platform from Wave 1 is reused — only solution-layer work remains.
• Subscriber ramp and churn in Sheet 8 are illustrative; replace with e& demand-model figures once available.
• Voice (STT/TTS) and WhatsApp BSP costs are estimates pending vendor quotes (Deepgram, ElevenLabs, e& BSP).
• Cloud cost depends on whether deployment is on e& OCI Dedicated Region / Azure CSP via e& / G42; revise once landing zone confirmed.

## 2. Roles & Rates
Roles & Daily Rates
IN PLAIN ENGLISH: This is the team. 10 people with different skills. The 'Internal cost' column is what each person costs us per day. The 'Bill rate' is what we'd charge for them.
Role | Seniority | Internal cost / day (USD) | Bill rate / day (USD) | Notes
Engagement / Programme Manager | Senior | 1000 | 1750 | Single point of contact to e&; weekly governance; commercial owner.
Solution Architect (Lead) | Principal | 1100 | 2100 | Owns reference architecture, multi-tenant design, latency budget, capability matrix.
AI / LLM Engineer — Orchestration & Reasoning | Senior | 900 | 1700 | Agent graph, FSM, tool-calling, memory, guardrails, Portkey integration.
Voice / Conversational Engineer | Senior | 850 | 1650 | Telephony (Toll Free 800), STT/TTS, WhatsApp/Web channels, Arabic/English NLP.
Data & Integration Engineer | Senior | 900 | 1550 | Connectors (CRM, calendar, payments), e& billing API, vector store, knowledge ingestion.
Frontend / UX Engineer | Mid | 750 | 1300 | Next.js tenant back office, onboarding, admin console, agent configuration UI.
DevOps / Platform Engineer | Senior | 950 | 1550 | Helm/Terraform, CI/CD, multi-tenant K8s, observability stack, secrets, cost guardrails.
QA Engineer | Mid | 700 | 1200 | Test packs, synthetic SMB data, automated regression, voice/chat acceptance tests.
Security / Compliance Lead | Senior | 1050 | 1750 | Tenant isolation, NESA / TDRA / ADDA controls, pen-test coordination.
Customer Success / Beta Ops Lead | Mid | 600 | 950 | Beta SMB recruitment & onboarding, feedback loops, runbooks, support escalation.
Total roles in plan: 10

## 3. Phase Staffing
Wave 1 — Phase Staffing
IN PLAIN ENGLISH: How many people work on each phase and how much of their time goes to this project. 15 weeks total, split into 6 phases. Scroll down to the yellow cells to change the numbers.
Role | P1 — Mobilisation & Foundations | P2 — Platform Build & Customer Agent SDD | P3 — Customer Agent Build | P4 — Internal Alpha & Hardening | P5 — Closed Beta & Production v1 | P6 — GA Launch & Hypercare | Total p-weeks
Phase duration (weeks) | 2 | 3 | 3 | 2 | 2 | 3 | —
Engagement / Programme Manager | 1 | 1.8 | 1.8 | 1.4 | 1.6 | 1.8 | 9.4
Solution Architect (Lead) | 2 | 3 | 2.4 | 1.2 | 0.8 | 0.9 | 10.3
AI / LLM Engineer — Orchestration & Reasoning | 1.2 | 3 | 6 | 4 | 1.4 | 1.2 | 16.8
Voice / Conversational Engineer | 0.8 | 2.4 | 6 | 2 | 1.4 | 0.9 | 13.5
Data & Integration Engineer | 1.2 | 2.4 | 3 | 1.6 | 1.2 | 0.9 | 10.3
Frontend / UX Engineer | 1 | 2.4 | 3 | 1.4 | 1 | 0.9 | 9.7
DevOps / Platform Engineer | 1.6 | 6 | 2.4 | 1.6 | 1.4 | 1.5 | 14.5
QA Engineer | 0 | 0 | 1.5 | 2 | 4 | 1.8 | 9.3
Security / Compliance Lead | 1 | 1.5 | 0.9 | 1.2 | 0.8 | 0.6 | 6
Customer Success / Beta Ops Lead | 0 | 0 | 1.2 | 1.2 | 2 | 2.1 | 6.5
Total person-weeks per phase | 9.8 | 22.5 | 28.2 | 17.6 | 15.6 | 12.6 | 106.3
EDITABLE — Headcount and Allocation % per Role per Phase
Headcount per phase (number of people).
Role | P1 — Mobilisation & Foundations | P2 — Platform Build & Customer Agent SDD | P3 — Customer Agent Build | P4 — Internal Alpha & Hardening | P5 — Closed Beta & Production v1 | P6 — GA Launch & Hypercare
Engagement / Programme Manager | 1 | 1 | 1 | 1 | 1 | 1
Solution Architect (Lead) | 1 | 1 | 1 | 1 | 1 | 1
AI / LLM Engineer — Orchestration & Reasoning | 1 | 1 | 2 | 2 | 1 | 1
Voice / Conversational Engineer | 1 | 1 | 2 | 1 | 1 | 1
Data & Integration Engineer | 1 | 1 | 1 | 1 | 1 | 1
Frontend / UX Engineer | 1 | 1 | 1 | 1 | 1 | 1
DevOps / Platform Engineer | 1 | 2 | 1 | 1 | 1 | 1
QA Engineer | 0 | 0 | 1 | 1 | 2 | 1
Security / Compliance Lead | 1 | 1 | 1 | 1 | 1 | 1
Customer Success / Beta Ops Lead | 0 | 0 | 1 | 1 | 1 | 1
Allocation % per phase (share of time on this programme).
Role | P1 — Mobilisation & Foundations | P2 — Platform Build & Customer Agent SDD | P3 — Customer Agent Build | P4 — Internal Alpha & Hardening | P5 — Closed Beta & Production v1 | P6 — GA Launch & Hypercare
Engagement / Programme Manager | 50% | 60% | 60% | 70% | 80% | 60%
Solution Architect (Lead) | 100% | 100% | 80% | 60% | 40% | 30%
AI / LLM Engineer — Orchestration & Reasoning | 60% | 100% | 100% | 100% | 70% | 40%
Voice / Conversational Engineer | 40% | 80% | 100% | 100% | 70% | 30%
Data & Integration Engineer | 60% | 80% | 100% | 80% | 60% | 30%
Frontend / UX Engineer | 50% | 80% | 100% | 70% | 50% | 30%
DevOps / Platform Engineer | 80% | 100% | 80% | 80% | 70% | 50%
QA Engineer | 0% | 0% | 50% | 100% | 100% | 60%
Security / Compliance Lead | 50% | 50% | 30% | 60% | 40% | 20%
Customer Success / Beta Ops Lead | 0% | 0% | 40% | 60% | 100% | 70%

## 4. Phase Effort & Cost
Wave 1 — What Does Each Person Cost Per Phase?
IN PLAIN ENGLISH: This multiplies 'how long they work' (Sheet 3) × 'their daily rate' (Sheet 2). The total at the bottom is our people cost for Wave 1: ~$472K.
INTERNAL COST (fully-loaded AIdeology cost)
Role | Cost / day | P1 — Mobilisation & Foundations | P2 — Platform Build & Customer Agent SDD | P3 — Customer Agent Build | P4 — Internal Alpha & Hardening | P5 — Closed Beta & Production v1 | P6 — GA Launch & Hypercare | Total cost | % of total
Engagement / Programme Manager | 1000 | 5000 | 9000 | 9000 | 7000 | 8000 | 9000 | 47000 | 9.962%
Solution Architect (Lead) | 1100 | 11000 | 16500 | 13200 | 6600 | 4400 | 4950 | 56650 | 12.01%
AI / LLM Engineer — Orchestration & Reasoning | 900 | 5400 | 13500 | 27000 | 18000 | 6300 | 5400 | 75600 | 16.02%
Voice / Conversational Engineer | 850 | 3400 | 10200 | 25500 | 8500 | 5950 | 3825 | 57375 | 12.16%
Data & Integration Engineer | 900 | 5400 | 10800 | 13500 | 7200 | 5400 | 4050 | 46350 | 9.825%
Frontend / UX Engineer | 750 | 3750 | 9000 | 11250 | 5250 | 3750 | 3375 | 36375 | 7.71%
DevOps / Platform Engineer | 950 | 7600 | 28500 | 11400 | 7600 | 6650 | 7125 | 68875 | 14.6%
QA Engineer | 700 | 0 | 0 | 5250 | 7000 | 14000 | 6300 | 32550 | 6.899%
Security / Compliance Lead | 1050 | 5250 | 7875 | 4725 | 6300 | 4200 | 3150 | 31500 | 6.677%
Customer Success / Beta Ops Lead | 600 | 0 | 0 | 3600 | 3600 | 6000 | 6300 | 19500 | 4.133%
Total internal cost per phase |  | 46800 | 105375 | 124425 | 77050 | 64650 | 53475 | 471775 | 100%

## 5. Other Costs
Wave 1 — Non-People Costs (software, cloud, travel, etc.)
IN PLAIN ENGLISH: Everything we spend that isn't salaries — cloud servers, AI APIs, WhatsApp, security tools, flights to the UAE, etc. Total: ~$154K.
Cost item | Unit cost | Quantity / months | Total cost | Phase trigger | Notes
Cloud / K8s dev + staging cluster (e& OCI / Azure CSP) | 6000 | 4 | 24000 | P1–P6 | Multi-tenant cluster footprint during build & beta. Production sized separately.
LLM Gateway licence (Portkey / equivalent) | 1500 | 4 | 6000 | P1–P6 | Routing, fallback, observability, cost guardrails across Azure OpenAI / Anthropic / OpenInnovation.
LLM API spend — build, alpha, beta | 4000 | 4 | 16000 | P2–P6 | Includes prompt engineering, regression test runs, beta tenant traffic.
STT / TTS API (Deepgram, ElevenLabs / Azure Speech) | 2500 | 4 | 10000 | P2–P6 | Voice agent training & beta. Arabic/English, low-latency.
WhatsApp BSP (e& or partner) — sandbox + tests | 1500 | 4 | 6000 | P2–P6 | Template approval, opt-in flows, message-rate tests on UAE numbers.
Observability stack (Grafana Cloud, Loki, Langfuse) | 1500 | 4 | 6000 | P1–P6 | Hosted observability for the AIdeology team; production stack runs in e& env.
CI/CD & repo hosting (GitHub Enterprise) | 800 | 4 | 3200 | P1–P6 | Pipelines, secrets, environments, security scanning.
Security tooling (SAST/DAST/SCA — Snyk / Checkmarx) | 2000 | 4 | 8000 | P1–P6 | Continuous static & dependency scanning.
Pen-test (third-party, before GA) | 25000 | 1 | 25000 | P5 | External pen-test prior to GA; required for production launch.
Travel — UAE (3 people × 5 days × 4 trips) | 9000 | 4 | 36000 | P1–P6 | On-site mobilisation, integration, beta kickoff, GA launch.
Marketing / launch event support | 8000 | 1 | 8000 | P6 | GA launch enablement: collateral, demo videos, launch event support.
Misc (printing, demos, contingency petty) | 1500 | 4 | 6000 | All | Petty cash for the engagement.
Total other costs (subtotal) |  |  | 154200

## 6. Wave 2-4 Build Costs
Waves 2-4 — Cost of the Next 5 Agents
IN PLAIN ENGLISH: After Wave 1, we build 5 more agents (Sales, Comms, Finance, Ops, People). The platform already exists, so each one is cheaper. This sheet shows the cost of each.
Role | Cost / day | Wave 2A — Sales Agent (CRM, lead, pipeline) | Wave 2B — Comms Hub (omnichannel inbox, campaigns) | Wave 3A — Finance Agent (invoicing, VAT, e& Pay) | Wave 3B — Ops Agent (tasks, SOP KB, service desk) | Wave 4 — People Agent (WPS, payroll, HR) | Total p-weeks (×days) | Notes
Engagement / Programme Manager | 1000 | 3 | 3 | 3 | 3 | 3 | 15 | Engagement coordination; lighter than Wave 1.
Solution Architect (Lead) | 1100 | 4 | 4 | 4 | 4 | 3 | 19 | Solution architect supports SDD spec & integration design per wave.
AI / LLM Engineer — Orchestration & Reasoning | 900 | 10 | 8 | 8 | 8 | 6 | 40 | Heaviest role per agent — orchestration, prompts, tools, evals.
Voice / Conversational Engineer | 850 | 4 | 8 | 2 | 2 | 0 | 16 | Comms Hub = heaviest voice; Sales = light voice; Finance/Ops = minimal voice; People = none.
Data & Integration Engineer | 900 | 10 | 8 | 12 | 8 | 10 | 48 | Connectors are wave-driver: Finance APIs, HR systems, tax. Most variable.
Frontend / UX Engineer | 750 | 6 | 6 | 6 | 6 | 6 | 30 | Tenant UI tweaks per agent + admin console.
DevOps / Platform Engineer | 950 | 3 | 3 | 3 | 3 | 3 | 15 | Per-wave deployment, observability hooks, cost guardrails.
QA Engineer | 700 | 4 | 4 | 4 | 4 | 4 | 20 | Test packs, regression, acceptance.
Security / Compliance Lead | 1050 | 3 | 3 | 4 | 3 | 4 | 17 | Higher for Finance & People (PII, payroll regs).
Customer Success / Beta Ops Lead | 600 | 3 | 3 | 3 | 3 | 3 | 15 | Pilot tenant onboarding & support per wave.
Total person-weeks per wave |  | 50 | 50 | 49 | 44 | 42 | 235
Personnel cost per wave (USD)
Item | Wave 2A — Sales Agent (CRM, lead, pipeline) | Wave 2B — Comms Hub (omnichannel inbox, campaigns) | Wave 3A — Finance Agent (invoicing, VAT, e& Pay) | Wave 3B — Ops Agent (tasks, SOP KB, service desk) | Wave 4 — People Agent (WPS, payroll, HR) | Total
Personnel cost |  | 219500 | 218500 | 216250 | 193000 | 184250 | 1031500
Other costs (per wave, ~30% of Wave 1 envelope) |  | 46260 | 46260 | 46260 | 46260 | 46260 | 231300
Total fully-loaded cost per wave |  | 265760 | 264760 | 262510 | 239260 | 230510 | 1262800

## 7. Pricing Summary
Pricing Summary — What We Charge e&
IN PLAIN ENGLISH: Takes our costs, adds a safety buffer (10%) and our profit margin (40%), and gives us the price we should charge e& for each wave.
Wave 1 — SMB Launch (Base Platform + Customer Agent)
Component | Value (USD) |  | Notes
Personnel cost — internal (sum of 6 phases) | 471775 |  | From Sheet 4 (cost basis).
Other costs — non-personnel | 154200 |  | From Sheet 5.
Subtotal — direct cost | 625975 |  | Personnel + non-personnel.
Contingency on direct cost | 62597.5 |  | % from Sheet 1.
Total fully-loaded cost | 688572.5 |  | Direct cost + contingency.
AIdeology margin on cost (grossed up) | 459048.3333 |  | Margin grossed up: price = cost / (1 - margin).
Price to e& — Wave 1 (Implementation Fee) | 1147620.8333 |  | Fixed-fee proposed for Wave 1.
Effective margin % | 40% |  | Should approximate target margin from Sheet 1.
Waves 2-4 — Per-Wave Pricing (Solution-layer only)
Wave | Total cost (USD) | Margin (USD) | Price to e& (USD)
Wave 2A — Sales Agent | 265760 | 217440 | 483200
Wave 2B — Comms Hub | 264760 | 216621.8182 | 481381.8182
Wave 3A — Finance Agent | 262510 | 214780.9091 | 477290.9091
Wave 3B — Ops Agent | 239260 | 195758.1818 | 435018.1818
Wave 4 — People Agent | 230510 | 188599.0909 | 419109.0909
Total Waves 2-4 (5 agents) | 1262800 | 1033200 | 2296000
Programme envelope (Wave 1 + Waves 2-4)
Component | Value (USD) |  | Notes
Wave 1 — Implementation fixed fee | 1147620.8333 |  | From Wave 1 stack above.
Waves 2-4 — Solution build fees (5 agents) | 2296000 |  | Sum of Wave 2A/2B/3A/3B/4.
Total fixed-fee envelope | 3443620.8333 |  | All implementation & build fees.
Risk reserve (held internally — not in price) | 34428.625 |  | Held at AIdeology level for genuine Wave-1 risk events.
Reality check — internal cost vs JSX commercial framework
Reference / scenario | Value (USD) |  | Notes
Internal Wave 1 price (this model, 40% margin) | 1147620.8333 |  | What we should charge to hit target margin.
JSX proposed implementation fee — low end | 150000 |  | Per current commercial framework: low end $150K (under our cost).
JSX proposed implementation fee — high end | 250000 |  | Per current commercial framework: high end $250K (still under our cost).
Gap vs our cost (low-end JSX) | -538572.5 |  | Loss on Wave 1 if we sell at $150K.
Gap vs our cost (high-end JSX) | -438572.5 |  | Loss on Wave 1 if we sell at $250K.
Years of rev-share needed to break even (high-end JSX, mid adoption) | 2.1578 |  | Wave 1 cost gap ÷ avg annual rev-share (Y1-Y3 mid). Indicative: rev-share ramps so payback is faster in later years.
Recommended commercial structures (3 options)
Option | Up-front fee | Rev-share % | Notes
A — Cost-plus (full margin up-front) | 1147620.8333 | 10% | Charge full implementation fee. Rev-share at 10% (low end). Best for AIdeology cash-flow but hardest to sell.
B — Hybrid (split) | 500000 | 18% | Up-front fee covers core platform cost; aggressive rev-share captures upside. Balanced.
C — Land & expand (JSX framework) | 250000 | 20% | Aggressive sell-in at $250K + 20% rev-share. Needs subscriber ramp + Wave 2-4 fees to recover Wave 1 cost.

## 8. Revenue Share Model
Revenue Share — Our Recurring Income
IN PLAIN ENGLISH: Every month, SMBs pay e& a subscription. We get 15% of that. As more SMBs sign up, this grows every year. This is the long-term prize on top of the fixed fees.
Subscriber ramp (paying SMB tenants — end of year)
Metric | Year 1 | Year 2 | Year 3 | Notes
Paying SMB tenants — end of year (mid) | 750 | 2250 | 4000 | Per JSX: 500-1,000 Y1, 1,500-3,000 Y2, 3,000-5,000+ Y3 (mid points).
Avg paying tenants over the year (mid) | 375 | 1500 | 3125 | Linear ramp assumption. Override if e& demand model differs.
ARPU per tenant (USD/month) | 60 | 65 | 70 | Mild upgrade assumption (cross-sell from Customer to Sales/Comms agents).
Gross subscription revenue (USD/year) | 270000 | 1170000 | 2625000 | Avg tenants × ARPU × 12 months. e& top-line.
Rev-share % to AIdeology (mid) | 15% | 15% | 15% | Sourced from Sheet 1 input (override per year if degressive tiers apply).
AIdeology rev-share revenue (USD/year) | 40500 | 175500 | 393750
Implementation & wave fees (recognised by year)
Item | Year 1 | Year 2 | Year 3 | Notes
Wave 1 implementation fee | 1147620.8333 | 0 | 0 | Recognised in Y1 across milestones.
Wave 2A — Sales Agent (50/50 Y1/Y2) | 241600 | 241600 | 0 | Wave 2 kicks off ~M9, finishes M16.
Wave 2B — Comms Hub (50/50 Y1/Y2) | 240690.9091 | 240690.9091 | 0
Wave 3A — Finance Agent (Y2) | 0 | 477290.9091 | 0 | Built in Y2.
Wave 3B — Ops Agent (Y2) | 0 | 435018.1818 | 0
Wave 4 — People Agent (Y3) | 0 | 0 | 419109.0909 | Built in Y3.
Subtotal — fees recognised | 1629911.7424 | 1394600 | 419109.0909
AIdeology total revenue (rev-share + fees)
Item | Year 1 | Year 2 | Year 3 | 3-Year Total
Rev-share revenue | 40500 | 175500 | 393750 | 609750
Implementation & wave fees | 1629911.7424 | 1394600 | 419109.0909 | 3443620.8333
Total AIdeology revenue | 1670411.7424 | 1570100 | 812859.0909 | 4053370.8333

## 9. Payment Milestones
Wave 1 — When Does e& Pay Us?
IN PLAIN ENGLISH: e& pays us in 4 instalments, each triggered by a milestone (kickoff, alpha, beta, launch). This also shows our cash-flow: when money comes in vs when we spend it.
# | Milestone / trigger | % of price | Target week | Amount (USD) | Acceptance criteria
1 | Mobilisation & SOW signature (kickoff) | 25% | T + 0 | 286905.2083 | M1 — Platform foundations stood up; team mobilised within 48h; SOW Schedule A traceability accepted.
2 | Customer Agent in dev + Internal Alpha | 25% | T + 6 wk | 286905.2083 | M2 + M3 — Voice/WhatsApp/web flows working end-to-end; alpha used by AIdeology + e& staff.
3 | Closed beta live (10–20 SMBs) | 30% | T + 9 wk | 344286.25 | M4 — Beta tenants in production; CSAT and CAC data flowing; escalation paths validated.
4 | GA launch + Wave-2 readiness | 20% | T + 13–15 wk | 229524.1667 | M5 + M6 — Production v1 hardened; security + Arabic/English acceptance tests passed; marketplace open.
| Sum check | 100% |  | 1147620.8333
Indicative monthly cash-flow — Wave 1 only (months from kickoff)
Item | M0 (kickoff) | M1 | M2 | M3 (beta) | M4 (GA)
Cash IN (payments from e&) | 286905.2083 | 0 | 286905.2083 | 344286.25 | 229524.1667
Cash OUT (AIdeology cost burn, est.) | 38820 | 128002.5 | 149550 | 192962.5 | 116640
Net cash flow | 248085.2083 | -128002.5 | 137355.2083 | 151323.75 | 112884.1667
Cumulative net cash flow | 248085.2083 | 120082.7083 | 257437.9167 | 408761.6667 | 521645.8333
Note: cash-out assumes uniform burn within month; refine if monthly invoicing differs from phase boundaries.

## 10. Sensitivity
What-If Scenarios — How Much Do We Earn?
IN PLAIN ENGLISH: What if fewer SMBs sign up? What if our rev-share is 10% instead of 15%? This grid shows our total 3-year revenue under 9 different scenarios (3 adoption levels × 3 rev-share rates).
A. Adoption scenarios — average paying tenants per year
Scenario | Year 1 (avg) | Year 2 (avg) | Year 3 (avg) | Notes
Low — slow ramp | 250 | 1000 | 2000 | Conservative: 500 EOY1, 1,500 EOY2, 2,500 EOY3.
Mid — baseline (per Sheet 8) | 375 | 1500 | 3125 | Baseline used in Sheet 8.
High — strong adoption | 500 | 2000 | 4500 | 1,000 EOY1, 3,000 EOY2, 5,500 EOY3.
Blended ARPU (USD/month, 3-year avg) | 65 |  |  | Editable. Used for sensitivity calcs below.
B. AIdeology 3-year rev-share revenue (USD) — Scenario × Rev-share %
Adoption scenario | 10% rev-share | 15% rev-share | 20% rev-share | Notes
Low — slow ramp | 253500 | 380250 | 507000 | 3-year cumulative AIdeology rev-share at fixed % rate.
Mid — baseline (per Sheet 8) | 390000 | 585000 | 780000 | 3-year cumulative AIdeology rev-share at fixed % rate.
High — strong adoption | 546000 | 819000 | 1092000 | 3-year cumulative AIdeology rev-share at fixed % rate.
C. Total AIdeology 3-year revenue (fees + rev-share)
Adoption scenario | 10% rev-share | 15% rev-share | 20% rev-share | Notes
Low — slow ramp | 3697120.8333 | 3823870.8333 | 3950620.8333 | Total = fixed-fee envelope (Sheet 7) + 3-year rev-share at chosen %.
Mid — baseline (per Sheet 8) | 3833620.8333 | 4028620.8333 | 4223620.8333 | Total = fixed-fee envelope (Sheet 7) + 3-year rev-share at chosen %.
High — strong adoption | 3989620.8333 | 4262620.8333 | 4535620.8333 | Total = fixed-fee envelope (Sheet 7) + 3-year rev-share at chosen %.